## Sheet1
S.No | Modules | Description | Estimation (In Hours)
1 | Database Table Creation | Table Creation for all modules | 2
2 | Project Architecture Creation | Project Architecture Creation 1. Project Architecture 2. Project Design Pattern. | 10
3 | Database Entity Framework | Database Entity Framework Creation in Code 1. Database Connectivity 2. Database Model and View Model Connectivity | 8
4 | Project Design Implementation | Need to Implement Design for Master Pages and Design Implementation | 4
5 | User Module 1. User Role (Add, Update, Delete, View) 2. User Master (Add, Update, Delete, View) 3. Function Master (Add, Update, Delete, View) 4. User Function Linking Role (Add, Update, Delete, View) 5. User Subscription Master (Add, Update, Delete, View) | Creating of Views, Models, View Models, Creation of API’s, Functions, Client Side and Server Side validations, Saving Data to Database, Alert Messages 1. User Role (Add, Update, Delete) : 4 Hours 2. User Master (Add, Update, Delete) : 4 Hours 3. Function Master (Add, Update, Delete) : 4 Hours 4. User Function Linking Role (Add, Update, Delete) : 4 Hours 5. User Subscription Master (Add, Update, Delete) : 4 Hours Complete Testing for all functionality : 4 Hours | 24
6 | User Authentication and User Authorization Role Wise | Need to Implement User Authentication and User Authorization to the application with testing. 1. User Authentication (Login, Logout, Forgot Password) : 8 Hours 2. User Authorization (Role Base) : 8 Hours | 12
7 | City, State and District Master Module 1. City Master (Add, Update, Delete, View) 2. State Master (Add, Update, Delete, View) 3. District Master (Add, Update, Delete, View) | Creating of Views, Models, View Models, Creation of API’s, Functions, Client Side and Server Side validations, Saving Data to Database, Alert Messages All activities. 1. City Master (Add, Update, Delete, View) : 4 Hours 2. State Master (Add, Update, Delete, View) : 4 Hours 3. District Master (Add, Update, Delete, View) : 4 Hours Complete Testing for all functionality : 2 Hours | 14
8 | Transport Master Module | Creating of Views, Models, View Models, Creation of API’s, Functions, Client Side and Server Side validations, Saving Data to Database, Alert Messages Additional Validations and Function to generate Transporter Bill No All activities. 1. Transport Master Module (Add, Update, Delete) : 10 Hours 2 .Complete Testing for all functionality : 2 Hours | 12
9 | GST Module 1. GST Master (Add, Update, Delete, View) 2. GST Rate Master (Add, Update, Delete, View) | Creating of Views, Models, View Models, Creation of API’s, Functions, Client Side and Server Side validations, Saving Data to Database, Alert Messages All activities. 1. GST Master (Add, Update, Delete, View) : 4 Hours 2. GST Rate Master (Add, Update, Delete, View) : 4 Hours 3. Testing of Complete Module : 2 Hours | 10
10 | Transporter Bill Generation 1. Bill Generation (Add, Update, Delete, View, Print, View Pending Bills) | Creating of Views, Models, View Models, Creation of API’s, Functions, Client Side and Server Side validations, Saving Data to Database, Alert Messages All activities. Additional Validations and Function to generate Transporter Bill No 1. Bill Generation (Add, Update, Delete, View, Print, Pending Bills : 32 Hours 2. Testing of Complete Module : 3 Hours | 35
11 | Upload Data from CSV File | Need to create a functionality to Read Data from CSV, Excel File and Save to Database | 16
12 | Save Data from Json Data Source | Need to create a functionality to Read Data from JSON and Save to Database | 16
.
Hourly Rate : 400 (Per Hour)
|  | Total No of Hours : | 163
|  | Total Price : | 65200